## Requirements
Requirements | Requirement | Description | Priority | Status
Requirement ID | Business Requirement | Description | Priority | Implementation
REQ-001 | Product Management | The system shall maintain product information including product ID, name, category, supplier, unit price, and reorder level. | High | SQLite / Power BI
REQ-002 | Inventory Tracking | The system shall maintain current stock quantities for each product. | High | SQLite / Power BI
REQ-003 | Low Stock Monitoring | The system shall identify products whose stock quantity is at or below the defined reorder level. | High | SQL / Power BI
REQ-004 | Sales Tracking | The system shall maintain sales transactions including product, date, quantity sold, and unit price. | Medium | SQLite
REQ-005 | Sales Reporting | The system shall provide total sales and sales analysis by product and category. | High | SQL / Power BI

## Implementation Plan
Phase | Task | Owner | Status
Phase | Activity | Responsible Role | Status
Requirements | Define business requirements | Implementation Specialist | Completed
Data Preparation | Prepare product, inventory, and sales data | Data Analyst | Completed
Database | Create SQLite database | Implementation Specialist | Completed
Database | Create tables and relationships | Implementation Specialist | Completed
SQL | Develop business queries | Data Analyst | Completed
Reporting | Connect Power BI to reporting data | Data Analyst | Completed
Reporting | Build inventory dashboard | Data Analyst | Completed