## Sheet1
Checklist ID | Category | Checklist Item | Status | Owner | Notes
GL-001 | Requirements | Business requirements documented | Completed | Implementation Specialist | Requirements documented and reviewed
GL-002 | Data | Product data prepared | Completed | Data Analyst | 10 product records prepared
GL-003 | Data | Inventory data prepared | Completed | Data Analyst | 10 inventory records prepared
GL-004 | Data | Sales data prepared | Completed | Data Analyst | 10 sales records prepared
GL-005 | Database | Database tables created | Completed | Implementation Specialist | Products, Inventory, and Sales tables created
GL-006 | Database | Database relationships verified | Completed | Implementation Specialist | Product relationships verified
GL-007 | Reporting | Power BI dashboard completed | Completed | Data Analyst | Dashboard and KPIs completed
GL-008 | Testing | UAT test cases completed | Completed | Implementation Specialist | 12 of 12 test cases passed
GL-009 | Documentation | User guide completed | Completed | Implementation Specialist | User guide prepared
GL-010 | Training | Client training guide completed | Completed | Implementation Specialist | Training material prepared
GL-011 | Support | Basic troubleshooting procedures documented | Completed | Implementation Specialist | Troubleshooting guide included
GL-012 | Go-Live | Solution ready for simulated go-live | Completed | Implementation Specialist
Go-Live Readiness: READY
UAT Result: 12 Passed / 0 Failed
Project Status: Implementation Completed – Portfolio Simulation
This checklist demonstrates that you understand the final validation and go-live stage of an implementation project.